## Product Backlog
L: Low
Product Backlog | [6 empty] | M: Medium
H: High
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Status | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Sign in | User | Sign in to the website | I can use full function of website | - Enter email and password - If users do not input one of 2 fields, Show notification "The email/ password is required" - If user input wrong email or password, show notification "Email/password is wrong" - If user input invalid email, show notification "Login failed! Invalid email" |  | M |  |  |  | Done | 1 | 8
PB02 | Sign up | User | Sign up an account | I can become a user and use full function of website | - Access to website - Fill out all of required information - If users do not input one of fields, show notification "The....is required!" - If users input invalid data, show notification "Invalid....!" - Password must contain at least 8 characters include 1 uppercase letter |  | M |  |  |  | Done | 1 | 8
PB03 | Change password | User | Change password | I can change my password to protect my account | - Enter old password correctly - Confirm change - Enter wrong old password, show notification "The old password does not match" - Enter new password - Press the OK button |  | M |  |  |  | Done | 3 | 6
PB04 | Connect Metamask Wallet | User | Connect Metamask Wallet | I want to connect my metamask wallet account to the website's system | - Access metamask to website - Enter password metamask to login wallet metamask - Accept connect to website |  | H |  |  |  | Done | 2 | 3
PB05 | Disconnect Metamask Wallet | User | Disconnect Metamask Wallet | I can disconnect between the system and the metamask wallet | - Click the button "disconnect" - This website has connected to your Metamask wallet |  | M |  |  |  | Done | 2 | 3
PB06 | Forgot password | User | Find my password | I can find my password when I forgot the current password | - Enter your email - The system will send OTP code to your email - Use OTP code to reset password - Confirm new password" |  | M |  |  |  | Done | 3 | 8
PB07 | Manage account | User | User account management | I can manage my information account | - Requires honesty and accuracy when changing information. |  | L |  |  |  | Done | 3 | 10
PB08 | List of ongoing auctions | User | View ongoing auctions | I can view a list of ongoing bids | - I can view a list of all ongoing bids on the website |  | H |  |  |  | Done | 3 | 35
PB09 | Create an auction | User | Create an auction | I can create auction | - The current amount in your metamask wallet must be greater than the amount you want to bid. - ETH balance in metamask wallet must be sufficient |  | H |  |  |  | Done | 2 | 20
PB010 | Bidding | User | Bid the item | I can bid on the item I want | - The current amount in your metamask wallet must be greater than the amount you want to bid. - Enter the price you want to bid - Confirm you want to bid with this amount? |  | H |  |  |  | Done | 3 | 42
PB11 | Search Auction | User | Search auction | I can search auction | - User must already have an account of the system |  | M |  |  |  | Done | 4 | 8
PB12 | Auction information after the end | User | See all the information in the auction after it ends | I can see who entered the auction, who won the auction along with the highest price | - After the auctions end - Click on "Information details" |  | H |  |  |  | Done | 4 | 30
PB13 | Logout | User | Logout of the system | I can log out of the system when not in use. | - Click the sign out button |  | M |  |  |  | Done | 2 | 2
PB14 | Sign in | Admin | Sign in to the website | I can use full function of website | - Enter email and password - If users do not input one of 2 fields, Show notification "The email/ password is required" - If user input wrong email or password, show notification "Email/password is wrong" - If user input invalid email, show notification "Login failed! Invalid email" |  | M |  |  |  | Done | 1 | 8
PB15 | List past auctions | Admin | View past auction | I can to see a list of past auctions | - Click on "Past Auctions" |  | H |  |  |  | Done | 4 | 25
PB16 | Logout | Admin | Logout of the system | I can log out of the system when not in use. | - Click the sign out button |  | M |  |  |  | Done | 2 | 2
PB17 | Change Password | Admin | Change my password | I can change my password to protect my account | - Press the "change password" button - Enter old password, enter new password, confirm new password - Press the OK button |  | M |  |  |  | Done | 3 | 6
PB18 | Forgot password | Admin | Find my password | I can find my password when I forgot the current password | - Enter your email - The system will send OTP code to your email - Use OTP code to reset password - Confirm new password |  | M |  |  |  | Done | 3 | 8
PB19 | List of ongoing auctions | Admin | View ongoing auctions | I can view a list of ongoing bids | - I can view a list of all ongoing bids on the website |  | H |  |  |  | Done | 3 | 35
PB20 | Manage auctions | Admin | Manage auction | I can view, refuse or accept auction requests | - Click the Manage auctions button, a list of auction requests appears |  | H |  |  |  | Done | 3 | 12
PB21 | Search Auction | Admin | Search auction | I can search auction | '- User must already have an account of the system |  | M |  |  |  | Done | 4 | 8
PB22 | View fraudulent transactions | Admin | View transaction | I can see if the transactions have been breached. | - After the auctions end - Click on "View fraudulent transaction" |  | H |  |  |  | Not yet | 4 | 25

## Main (hidden)
Project | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint # | Start | End | Status | Work / Estimates Committed | Work spent Delivered | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | 1 |  |  | Complete | 3 | 3
[6 empty] | 2 |  |  | In Progress | 25 | 23
3
4
5
6

## User Stories
ID | Theme | As a/an | I want to | So that.. | Acceptance Criteria | Priority | Status
PB01 | Sign in | User | Sign in to website | I can use full funciton of website | - Enter email and password - If users do not input one of 2 fields, Show notification "The email/ password is required" - If user input wrong email or password, show notification "Email/password is wrong" - If user input invalid email, show notification "Login failed! Invalid email" | M | Done
PB02 | Sign up | User | Sign up an account | I can become a user and use full function of website | - Access to website - Fill out all of required information - If users do not input one of fields, show notification "The....is required!" - If users input invalid data, show notification "Invalid....!" - Password must contain at least 8 characters include 1 uppercase letter | M | Done
PB03 | Connect Wallet | User | Connect Wallet Metamask | I can connect the metamask wallet account to the system. | - Access metamask to website - Enter password metamask to login wallet metamask - Accept connect to website | H | Done
PB04 | Disconnect Wallet | User | Disconnect Wallet Metamask | I can disconnect between the system and the metamask wallet | - Can disconnect after connected to the metamask wallet - Click "Disconnect" button | M | Done
PB05 | Change Password | User | Change password | I can change my password to protect my account | - Enter old password correctly - Confirm change - Enter wrong old password, show notification "The old password does not match" - Enter new password - Press the OK button | M | Done
PB06 | Forgot password | User | Find my password | I can find my password when I forgot the current password | - Enter your email - The system will send OTP code to your email - Use OTP code to reset password - Confirm new password | M | Done
PB07 | Manage account | User | User account management | I want to manage my information account | - I can edit and update my account information - I can delete my account | L | Done
PB08 | List of ongoing auctions | User | View ongoing auctions | I can view a list of ongoing bids | - Access to website | M | Done
PB09 | Create an auction | User | Create an auction | I can create auction | - The current amount in your metamask wallet must be greater than the amount you want to bid. - ETH balance in metamask wallet must be sufficient | H | Done
PB10 | Bidding | User | Bidding the item | I can bid on the item I want | - Must connect to metamask wallet - Must have a balance greater than the starting price - Enter the price you want to bid - Confirm you want to bid with this amount? | H | Done
PB11 | Search auction | User | Search auction | I can search auction | - User must already have an account of the system | M | Done
PB12 | Auction information after the end | User | See all the information in the auction after it ends | I can see who entered the auction, who won the auction along with the highest price | - After the auctions end - Click on "Information details" | H | Done
PB13 | Log out | User | Logout of the system | I can log out of the system when not in use. | - Click the sign out button | M | Done
ID | Theme | As a/an | I want to | So that.. | Acceptance Criteria | Priority | Status
PB14 | Sign in | Admin | Sign in the system | I can use full funciton of website | - Enter email and password - If users do not input one of 2 fields, Show notification "The email/ password is required" - If user input wrong email or password, show notification "Email/password is wrong" - If user input invalid email, show notification "Login failed! Invalid email" | M | Done
PB15 | List Past Auctions | Admin | View list past auctions | I can view list past auctions | - Auctions must have been closed | M | Done
PB16 | Logout | Admin | Logout of the system | I can log out of the system when not in use. | - Click the sign out button | M | Done
PB17 | Change password | Admin | Change my password | I can change my password to protect my account | - Enter old password correctly - Confirm change - Enter wrong old password, show notification "The old password does not match" - Enter new password - Press the OK button | M | Done
PB18 | Forgot password | Admin | Find my password | I can find my password when I forgot the current password | - Enter your email - The system will send OTP code to your email - Use OTP code to reset password - Confirm new password" | M | Done
PB19 | List ongoing auctions | Admin | View ongoing auctions | I can view a list of ongoing bids | - Access to website - Login admin's account | H | Done
PB20 | Manage Auctions | Admin | Manage auctions | I can accept/reject auction openings from users. | - Accept: For proposals that meet the required standards of the system. - Reject: For proposals that do not meet the requirements of the system. | H | Done
PB21 | Search auction | Admin | Search auction | I can search auction | - User must already have an account of the system | M | Done
PB22 | View transaction | Admin | View transaction | I can see the list of fraudulent auctions | - After the auctions end - Click on "View fraudulent transaction" | H | Not yet

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 1 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
[7 empty] | Remaining work to be done. | Total number of hours you spent on the task. Your effort | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13
1.1 |  | Sprint kick-off meeting | All members | Done | 4 | 3 | 1 | 3 | -1 | Day 1: 3
1.2 |  | Update Database Design Document | An, Bao | Done | 5 | 8 | -3 | 8 | 3 | Day 1: 4; Day 2: 4
1.3 |  | Update Architecture Design Document | Huy, Ai | Done | 10 | 8 | 2 | 8 | -2 | Day 2: 4; Day 3: 2; Day 4: 2
1.4 |  | Update Product Backlog | All members | Done | 6 | 8 | -2 | 8 | 2 | Day 3: 3; Day 4: 3; Day 5: 2
1.5 |  | Update User Story | Ai, Bao | Done | 8 | 7 | 1 | 7 | -1 | Day 3: 2; Day 4: 3; Day 5: 2
1.6 |  | Update Interface Design Document | Bao, Huy | Done | 5 | 8 | -3 | 8 | 3 | Day 4: 2; Day 5: 2; Day 6: 4
1.7 |  | Create Test Plan for Sprint 1 | An, Huy | Done | 4 | 5 | -1 | 5 | 1 | Day 5: 3; Day 6: 2
1.8 |  | Design Testcase for Sprint 1 | An, Huy | Done | 8 | 7 | 1 | 7 | -1 | Day 7: 4; Day 8: 3
1.9 |  | [FE] Home Page | Huy | Done | 18 | 20 | -2 | 20 | 2 | Day 6: 2; Day 7: 2; Day 8: 4; Day 9: 8; Day 10: 4
1.1 |  | [FE] Sign In Page | Bao | Done | 8 | 9 | -1 | 9 | 1 | Day 6: 3; Day 7: 4; Day 8: 2
1.11 |  | [FE] SignUp Page | Bao | Done | 8 | 7 | 1 | 7 | -1 | Day 8: 3; Day 9: 4
1.12 |  | Test for Sprint 1 | An | Done | 10 | 13 | -3 | 13 | 3 | Day 7: 2; Day 8: 4; Day 9: 3; Day 10: 4
1.13 |  | Fix bug and re-test | Bao, Huy | Done | 5 | 7 | -2 | 7 | 2 | Day 10: 2; Day 11: 5
1.14 |  | Sprint Review meeting | All members | Done | 8 | 6 | 2 | 6 | -2 | Day 12: 6
1.15 |  | Sprint Retrospective | All members | Done | 3 | 3 | 0 | 3 | 0 | Day 13: 3
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
|  |  |  | Total | 110 | 119 | -9 | 119 | 9 | 7 | 8 | 7 | 10 | 9 | 11 | 12 | 16 | 15 | 10 | 5 | 6 | 3
|  |  |  | Estimate | [5 empty] | 100.8333 | 91.6667 | 82.5 | 73.3333 | 64.1667 | 55 | 45.8333 | 36.6667 | 27.5 | 18.3333 | 9.1667 | 0
| Work hours per day: | 9.1667 |  | Burn down | [5 empty] | 103 | 95 | 88 | 78 | 69 | 58 | 46 | 30 | 15 | 5 | 0 | -6 | -9
|  |  |  | Burn up | [5 empty] | 7 | 15 | 22 | 32 | 41 | 52 | 64 | 80 | 95 | 105 | 110 | 116 | 119
Note on B7: ====== ID#AAAAhMPCaOc jan samuelsson (2022-10-14 02:48:54) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAhMPCaOU jan samuelsson (2022-10-14 02:48:54) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.
Note on H7: ====== ID#AAAAhMPCaOg jan samuelsson (2022-10-14 02:48:54) Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.

## Sprint 2 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  | Only update one time. When task is done.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
Remaining
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
2.1 |  | Sprint kick-off meeting | All members | Done | 4 | 4 | 0 | 4
2.2 |  | Update Database Design Document | All members | Done | 4 | 4 | 0 | 4
2.3 |  | Update Architecture Design Document | All members | Done | 4 | 4 | 0 |  | 2 | 2
2.4 |  | Create Test Plan for Sprint 2 | An, Huy | Done | 4 | 6 | -2 |  | 2 | 2 | 2
2.5 |  | Design Test Case for Sprint 2 | An, Huy | Done | 8 | 7 | 1 |  |  | 2 | 2 | 3
2.6 |  | [BE] Write Smart Contract | Ai | Done | 20 | 21 | -1 |  | 2 | 4 | 4 | 4 | 4 | 3
2.7 |  | [BE] Connect Metamask Wallet | Ai | Done | 3 | 1 | 2 | [6 empty] | 1
2.8 |  | [BE] Disconnect Metamask Wallet | Ai | Done | 3 | 2 | 1 | [7 empty] | 2
2.9 |  | [FE] Logout | Huy | Done | 2 | 2 | 0 | [5 empty] | 2
2.1 |  | [BE] Build Database | An | Done | 8 | 8 | 0 |  |  |  |  | 3 | 3 | 2
2.11 |  | [BE] Deploy Smart Contract on Goerli testnet | Ai | Done | 4 | 4 | 0 | [7 empty] | 4
2.12 |  | [FE] Create an auction | Bao | Done | 5 | 4 | 1 | [8 empty] | 2 | 2
2.13 |  | [BE] Create an auction | Ai | Done | 15 | 21 | -6 | [8 empty] | 6 | 6 | 6 | 3
2.14 |  | Test for Sprint 2 | An | Done | 12 | 10 | 2 | [5 empty] | 4 | 4 | 2
2.15 |  | Fix bug and re-test | Bao, Huy | Done | 5 | 4 | 1 | [8 empty] | 2 | 2
2.16 |  | Sprint Review meeting | All members | Done | 4 | 4 | 0 | [10 empty] | 4
2.17 |  | Sprint Retrospective | All members | Done | 3 | 3 | 0 | [11 empty] | 3
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 108 | 109 | -1 | 8 | 6 | 10 | 8 | 10 | 13 | 10 | 8 | 10 | 10 | 10 | 6
|  |  |  | Estimate |  |  |  | 99 | 90 | 81 | 72 | 63 | 54 | 45 | 36 | 27 | 18 | 9 | 0
| Work hours per day: | 9 |  | Burn down |  |  |  | 100 | 94 | 84 | 76 | 66 | 53 | 43 | 35 | 25 | 15 | 5 | -1
|  |  |  | Burn up |  |  |  | 8 | 14 | 24 | 32 | 42 | 55 | 65 | 73 | 83 | 93 | 103 | 109

## Sprint 3 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  | Only update one time. When task is done.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
Remaining
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22
3.1 |  | Sprint kick-off meeting | All members | Done | 4 | 3 | 1 | 3
3.2 |  | Update Architecture Design Document | Ai | Done | 4 | 5 | -1 | 2 | 3
3.3 |  | Update Interface Design Document | Bao, Huy | Done | 16 | 16 | 0 | 2 | 6 | 6 | 2
3.4 |  | Update Test Plan for Sprint 3 | An, Huy | Done | 7 | 7 | 0 | 2 | 3 | 2
3.5 |  | Design Test Case for Sprint 3 | An, Huy | Done | 13 | 16 | -3 |  |  |  | 6 | 4 | 4 | 2
3.6 |  | [FE] Forgot password | Huy | Done | 8 | 8 | 0 |  |  |  |  | 2 | 2 | 4
3.7 |  | [FE] Change password | Bao | Done | 6 | 13 | -7 |  |  |  |  | 4 | 4 | 3 | 2
3.8 |  | [BE] List of ongoing auctions | Ai | Done | 20 | 23 | -3 |  |  |  | 4 | 4 | 6 | 6 | 3
3.9 |  | [FE] List of ongoing auctions | Huy, Bao | Done | 15 | 15 | 0 | [7 empty] | 3 | 4 | 2 | 3 | 3
3.1 |  | [FE] Manage auctions | Huy, Bao | Done | 12 | 12 | 0 | [10 empty] | 2 | 3 | 5 | 2
3.11 |  | [BE] Update Smart Contract | Ai | Done | 15 | 15 | 0 | [6 empty] | 2 | 3 | 4 | 4 | 2
3.12 |  | [BE] Deploy Smart Contract on Goerli testnet again | Ai | Done | 1 | 1 | 0 | [10 empty] | 1
3.13 |  | [BE] Create API to CRUD users | An | Done | 30 | 35 | -5 | [6 empty] | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4
3.14 |  | [BE] Bidding | Ai | Done | 26 | 38 | -12 | [8 empty] | 4 | 4 | 3 | 6 | 6 | 7 | 3 | 5
3.15 |  | [FE] Bidding | Huy | Done | 16 | 12 | 4 | [13 empty] | 3 | 4 | 2 | 3
3.16 |  | [FE] Profile | Huy, Bao | Done | 30 | 25 | 5 | [13 empty] | 4 | 4 | 6 | 4 | 4 | 3
3.17 |  | [FE] Edit Profile | Bao | Done | 20 | 15 | 5 | [13 empty] | 2 | 4 | 3 | 4 | 2
3.18 |  | Test for Sprint 3 | An | Done | 28 | 33 | -5 | [8 empty] | 2 | 2 | 3 |  |  | 3 | 4 | 3 | 3 | 4 | 3 | 4 | 2
3.19 |  | Fix bug and re-test | Huy, An | Done | 16 | 19 | -3 | [11 empty] | 2 | 4 | [5 empty] | 4 | 6 | 3
3.2 |  | Sprint Review meeting | All members | Done | 4 | 6 | -2 | [20 empty] | 4 | 2
3.21 |  | Sprint Retrospective | All members | Done | 3 | 2 | 1 | [21 empty] | 2
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 294 | 319 | -25 | 9 | 12 | 8 | 12 | 14 | 16 | 21 | 14 | 18 | 16 | 18 | 18 | 19 | 25 | 23 | 19 | 14 | 10 | 10 | 10 | 9 | 4
|  |  |  | Estimate |  |  |  | 280.6364 | 267.2727 | 253.9091 | 240.5455 | 227.1818 | 213.8182 | 200.4545 | 187.0909 | 173.7273 | 160.3636 | 147 | 133.6364 | 120.2727 | 106.9091 | 93.5455 | 80.1818 | 66.8182 | 53.4545 | 40.0909 | 26.7273 | 13.3636 | -9.5923e-14
| Work hours per day: | 13.3636 |  | Burn down |  |  |  | 285 | 273 | 265 | 253 | 239 | 223 | 202 | 188 | 170 | 154 | 136 | 118 | 99 | 74 | 51 | 32 | 18 | 8 | -2 | -12 | -21 | -25
|  |  |  | Burn up |  |  |  | 9 | 21 | 29 | 41 | 55 | 71 | 92 | 106 | 124 | 140 | 158 | 176 | 195 | 220 | 243 | 262 | 276 | 286 | 296 | 306 | 315 | 319

## Sprint 4 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  | Only update one time. When task is done.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
Remaining
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22
4.1 |  | Sprint kick-off meeting | All members | Done | 4 | 4 | 0 | 4
4.2 |  | Update Architecture Design Document | Ai | Done | 7 | 7 | 0 | 4 | 3
4.3 |  | Update Interface Design Document | Bao | Done | 4 | 4 | 0 |  | 4
4.4 |  | Update Test Plan | An, Huy | Done | 5 | 5 | 0 |  | 5
4.5 |  | Design Test Case for Sprint 4 | An, Huy | Done | 10 | 13 | -3 |  | 2 | 3 | 4 | 4
4.7 |  | [BE] List past auctions | Ai | Done | 25 | 31 | -6 |  | 1 | 6 | 4 | 4 | 6 | 6 | 4
4.8 |  | [FE] List past auctions | Huy, Bao | Done | 10 | 13 | -3 |  |  |  |  | 2 | 4 | 6 | 1
4.9 |  | [FE] Search Auction | Huy, Bao | Done | 8 | 8 | 0 | [8 empty] | 4 | 4
4.1 |  | [BE] Check Auction cheats | Ai | Not yet | 25 | 0 | 25
4.11 |  | [FE] Manage user accounts | Huy, Bao | Done | 10 | 12 | -2 | [10 empty] | 2 | 4 | 4 | 2
4.12 |  | [BE] Reveal Auction | Ai | Done | 25 | 24 | 1 | [6 empty] | 4 | 4 | 4 | 4 | 4 | 4
4.13 |  | [FE] Auction information after the end | Huy, Bao | Done | 10 | 9 | 1 | [10 empty] | 3 | 3 | 3
4.14 |  | [BE] Auction information after the end | Ai | Done | 20 | 20 | 0 | [12 empty] | 4 | 4 | 4 | 2 | 4 | 2
4.15 |  | Test for Sprint 4 | An | Done | 15 | 15 | 0 | [15 empty] | 4 | 4 | 4 | 3
4.16 |  | Fix bug and re-test | Bao, Huy | Done | 20 | 22 | -2 | [14 empty] | 4 | 2 | 4 | 4 | 4 | 4
4.17 |  | Sprint Review meeting | All members | Done | 6 | 5 | 1 | [20 empty] | 5
4.18 |  | Sprint Retrospective | All members | Done | 3 | 3 | 0 | [21 empty] | 3
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 207 | 195 | 12 | 8 | 15 | 9 | 8 | 10 | 10 | 16 | 9 | 8 | 8 | 9 | 11 | 11 | 6 | 8 | 8 | 12 | 10 | 7 | 4 | 5 | 3
|  |  |  | Estimate |  |  |  | 197.5909 | 188.1818 | 178.7727 | 169.3636 | 159.9545 | 150.5455 | 141.1364 | 131.7273 | 122.3182 | 112.9091 | 103.5 | 94.0909 | 84.6818 | 75.2727 | 65.8636 | 56.4545 | 47.0455 | 37.6364 | 28.2273 | 18.8182 | 9.4091 | 5.3291e-14
| Work hours per day: | 9.4091 |  | Burn down |  |  |  | 199 | 184 | 175 | 167 | 157 | 147 | 131 | 122 | 114 | 106 | 97 | 86 | 75 | 69 | 61 | 53 | 41 | 31 | 24 | 20 | 15 | 12
|  |  |  | Burn up |  |  |  | 8 | 23 | 32 | 40 | 50 | 60 | 76 | 85 | 93 | 101 | 110 | 121 | 132 | 138 | 146 | 154 | 166 | 176 | 183 | 187 | 192 | 195

## Sprint 2 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 4 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Impediment (hidden)
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## References (hidden)
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms

## Retrospective (hidden)
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks